## Sheet1
| Use Case Lines | UUCW | Actor Weight | Subsystem
1. Register | 2 | 5 | 3
2. Log in | 3 | 5 | 3
3. Manage Profile | 7 | 10 | 3 | 4
4. Billing | 3 | 5 | 3 | 2
5. Facebook | 3 | 5 | 3 | 2
6. Confirm Trip | 6 | 10 | 3
7. Offer Ride | 4 | 10 | 3 | 2
8. Accept a rider | 5 | 10 | 3
9. Cancel Drive | 2 | 5 | 3
10. Start Trip | 2 | 5 | 3
11. Request Ride | 4 | 10 | 3
12. Cancel Ride | 3 | 5 | 3
13. Monitor Trips | 8 | 15 | 3
14. Schedule Repeated Offers and Requests | 6 | 10 | 3
15. Handle Emergency | 0 | 5
16. Follow-up to resolve problems or gather feedback. | 5 | 10
17. Analyze and Manage Performance | 8 | 15 | 2
|  | 140 |  | 54
Technical Complexity Factors | Weight | Assessment | Impact
Distributed system | 2 | 4 | 8
Performance objectives | 2 | 3 | 6
End-user efficiency | 1 | 4 | 4
Complex processing | 1 | 3 | 3
Reusable code | 1 | 0 | 0
Easy to install | 0.5 | 1 | 0.5
Easy to use | 0.5 | 4 | 2
Portable | 2 | 3 | 6
Easy to change | 1 | 3 | 3
Concurrent use | 1 | 4 | 4
Security | 1 | 1 | 1
Access for third parties | 1 | 0 | 0
Training needs | 1 | 0 | 0
Total (TFactor) |  |  | 37.5
TCF |  |  | 0.975
Enviormental Factors |  |  |  | Bad Signs
Familiar with the development process | 1.5 | 3 | 4.5 | 0
Application experience | 0.5 | 4 | 2 | 0
Object-oriented experience | 1 | 3 | 3 | 0
Lead analyst capability | 0.5 | 3 | 1.5 | 0
Motivation | 1 | 2 | 2 | 1
Stable requirements | 2 | 1 | 2 | 1
Part-time staff | -1 | 2 | -2 | 0
Difficult programming language | -1 | 1 | -1 | 0
Total (Efactor) |  |  | 12 | 2
EF |  |  | 1.04
UCP |  |  | 196.716
Hours |  |  | 3934.32
Programmer-weeks |  |  | 131.144
Number of programmers | 3
Development time (weeks) |  |  | 43.7147