## Staffing Model
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | [13 empty] | PM | Architecture | Requirements | Creative & UI | Data | Security | Design (Java & Int.) | JSP Build & Unit Test | Java Build & Unit Test | Test (CIT & SIT) | Other | Total
|  | Dec '01 |  |  |  | Jan '02 |  |  |  | Feb '02 |  |  |  | Mar '02 |  |  |  |  | Apr '02 |  |  |  | May '02 |  |  |  |  | Jun '02 |  |  |  | Jul '02 |  |  |  | Aug '02 |  |  |  | Sept '02 |  |  |  | Oct '02
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Project Startup | bar: Dec '01 4 to Jan '02 2
Content Assessment | bar: Jan '02 3 to Feb '02 1
Content Extract Program | bar: Jan '02 3 to Feb '02 1
Content Target Matrix | bar: Feb '02 2
Content Parse/Restructure | bar: Feb '02 2 to Feb '02 4
CM Use Cases | bar: Mar '02 1 to Mar '02 2
CM Workflow Impl | bar: Mar '02 3 to Mar '02 5
Tag/Title Tool Development | bar: Mar '02 1 to Mar '02 2
Tag/Title Content | bar: Mar '02 3 to Aug '02 2
Site Map | bar: Jan '02 3 to Feb '02 1
Architecture Overview | bar: Jan '02 3 to Feb '02 1
Development System Setup | bar: Jan '02 4 to Feb '02 1
QA System Setup | bar: Feb '02 2 to Feb '02 3
Production System Setup | bar: Jun '02 3 to Jul '02 2
Usability Testing - Planning | bar: Feb '02 4 to Mar '02 3
Usability Testing - Execution | bar: Mar '02 4 to Apr '02 2
Integrated Model Setup | bar: Feb '02 2 to Feb '02 3
Wireframe Model | bar: Feb '02 2 to May '02 2
Use Cases | bar: Feb '02 3 to May '02 3
CM Specification | bar: Feb '02 4 to May '02 4
Visual Design Studies (Level 2) | bar: Jan '02 4 to Feb '02 4
Visual Designs | bar: Mar '02 1 to May '02 5
Style Guide | bar: Jun '02 1 to Jun '02 3
Cut, Tag, Optimize | bar: Mar '02 3 to Jun '02 1
Develop HTML | bar: Mar '02 4 to Jun '02 2
CM Bare Bones impl | bar: Mar '02 1 to Jun '02 1
CM Impl on Designed Pages | bar: Mar '02 5 to Jun '02 3
Content Creation | bar: Feb '02 3 to Mar '02 2
Application Design Activities | bar: Feb '02 2 to Apr '02 4
Application Development | bar: Apr '02 1 to Jun '02 3
Test Support | bar: Jun '02 4 to Aug '02 2
Test Planning | bar: Feb '02 2 to Feb '02 3
Test Script Writing | bar: Feb '02 4 to May '02 4
Functional Test | bar: Apr '02 1 to Jul '02 2
User Acceptance Test | bar: Jul '02 3 to Aug '02 2
Volume Test | bar: Jul '02 3 to Aug '02 2
Create Training Materials | bar: Jun '02 2 to Jun '02 3
Training | bar: Jun '02 4 to Jul '02 2
Cutover | [47 empty] | 2001 Hours | 2002 Hours | Total Hours | 2001 Hours by Band |  |  |  |  | 2002 Hours by Band |  |  |  |  | 1360 | 1360 | 720 | 0 | 0 | 0 | 1048 | #REF! | #REF! | #REF! | 432 | #REF! | bar: Aug '02 3
[51 empty] | 10 | 9 | 8 | 7 | 6 | 10 | 9 | 8 | 7 | 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CM Lead 1 | 9 |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [9 empty] | 40 | 680 | 720 |  | 40 |  |  |  |  | 680
CM Lead 2 | 8 | Dec '01 4: 40; Jan '02 1: 40; Jan '02 2: 40; Jan '02 3: 40; Jan '02 4: 40; Feb '02 1: 40; Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40 | 40 | 400 | 440 |  |  | 40 |  |  |  |  | 400
CM Junior 1 | 7 | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [9 empty] | 0 | 1048 | 1048 |  |  |  | 0 |  |  |  |  | 1048
CM Junior 2 | 7 | Jan '02 3: 40; Jan '02 4: 40; Feb '02 1: 40; Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40 | 0 | 440 | 440 |  |  |  | 0 |  |  |  |  | 440
DBA | 7 | [6 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [9 empty] | 0 | 496 | 496 |  |  |  | 0 |  |  |  |  | 496
[48 empty] | 0 | 0
Application Architect | 9 | Jan '02 2: 40; Jan '02 3: 40; Jan '02 4: 40; Feb '02 1: 40; Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40 | 0 | 680 | 680 |  | 0 |  |  |  |  | 680
Application Developer Lead | 8 | [5 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 8 | [9 empty] | 0 | 1248 | 1248 |  |  | 0 |  |  |  |  | 1248
Application Developer 1 | 7 | Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40 | 0 | 600 | 600 |  |  |  | 0 |  |  |  |  | 600
Application Developer 2 | 7 | Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40 | 0 | 600 | 600 |  |  |  | 0 |  |  |  |  | 600
Application Developer 3 | 7 | Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40 | 0 | 600 | 600 |  |  |  | 0 |  |  |  |  | 600
Infrastructure Architect | 10 | Jan '02 3: 24; Jan '02 4: 24; Feb '02 1: 24; Feb '02 2: 24; Feb '02 3: 24; Jun '02 3: 8; Jun '02 4: 8; Jul '02 1: 8; Jul '02 2: 8; Aug '02 3: 8 | 0 | 160 | 160 | 0 |  |  |  |  | 160
[48 empty] | 0 | 0
IA Lead | 8 | Dec '01 4: 40; Jan '02 1: 40; Jan '02 2: 40; Jan '02 3: 40; Jan '02 4: 40; Feb '02 1: 40; Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40 | 40 | 760 | 800 |  |  | 40 |  |  |  |  | 760
IA 1 | 7 | Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 32; May '02 4: 24; May '02 5: 16; Jun '02 1: 8; Jun '02 2: 8; Jun '02 3: 8; Jun '02 4: 8; Jul '02 1: 8; Jul '02 2: 8; Jul '02 3: 8; Jul '02 4: 8; Aug '02 1: 8; Aug '02 2: 8 | 0 | 712 | 712 |  |  |  | 0 |  |  |  |  | 712
IA 2 | 7 | Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40 | 0 | 520 | 520 |  |  |  | 0 |  |  |  |  | 520
IA 3 | 7 | Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40 | 0 | 400 | 400 |  |  |  | 0 |  |  |  |  | 400
IA 4 | 7 | Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40 | 0 | 400 | 400 |  |  |  | 0 |  |  |  |  | 400
[48 empty] | 0 | 0
Front End Designer | 7 | Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 8; May '02 4: 8; May '02 5: 8; Jun '02 1: 8; Jun '02 2: 8; Jun '02 3: 8; Jun '02 4: 8; Jul '02 1: 8; Jul '02 2: 8; Jul '02 3: 8; Jul '02 4: 8; Aug '02 1: 8; Aug '02 2: 8 | 0 | 624 | 624 |  |  |  | 0 |  |  |  |  | 624
[48 empty] | 0 | 0
Art Director | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [10 empty] | 8 | 832 | 840 |  |  | 8 |  |  |  |  | 832
Designer 1 | 7 | Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40 | 0 | 520 | 520 |  |  |  | 0 |  |  |  |  | 520
[48 empty] | 0 | 0
Production Specialist | 7 | Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 8; Jun '02 3: 8; Jun '02 4: 8; Jul '02 1: 8; Jul '02 2: 8; Jul '02 3: 8 | 0 | 568 | 568 |  |  |  | 0 |  |  |  |  | 568
[48 empty] | 0 | 0
Content Strategist | 7 | Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40 | 0 | 160 | 160 |  |  |  | 0 |  |  |  |  | 160
Tag/Title Resource 1 | 6 | Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40; Jul '02 3: 40; Jul '02 4: 40; Aug '02 1: 40; Aug '02 2: 40 | 0 | 1040 | 1040 |  |  |  |  | 0 |  |  |  |  | 1040
Tag/Title Resource 2 | 6 | Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40; Jul '02 3: 40; Jul '02 4: 40; Aug '02 1: 40; Aug '02 2: 40 | 0 | 1040 | 1040 |  |  |  |  | 0 |  |  |  |  | 1040
Tag/Title Resource 3 | 6 | Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40; Jul '02 3: 40; Jul '02 4: 40; Aug '02 1: 40; Aug '02 2: 40 | 0 | 1040 | 1040 |  |  |  |  | 0 |  |  |  |  | 1040
Tag/Title Resource 4 | 6 | Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40; Jul '02 3: 40; Jul '02 4: 40; Aug '02 1: 40; Aug '02 2: 40 | 0 | 1040 | 1040 |  |  |  |  | 0 |  |  |  |  | 1040
Tag/Title Resource 5 | 6 | Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40; Jul '02 3: 40; Jul '02 4: 40; Aug '02 1: 40; Aug '02 2: 40 | 0 | 1040 | 1040 |  |  |  |  | 0 |  |  |  |  | 1040
[48 empty] | 0 | 0 | 0
Test Manager | 8 | Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40; Jul '02 3: 40; Jul '02 4: 40; Aug '02 1: 40; Aug '02 2: 40 | 0 | 1080 | 1080 |  |  | 0 |  |  |  |  | 1080
LoadRunner Scripter | 8 | Feb '02 4: 40; Mar '02 1: 40; Mar '02 2: 40; Mar '02 3: 40; Mar '02 4: 40; Mar '02 5: 40; Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40 | 0 | 840 | 840 |  |  | 0 |  |  |  |  | 840
Tester 1 | 6 | Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40 | 0 | 600 | 600 |  |  |  |  | 0 |  |  |  |  | 600
Tester 2 | 6 | Apr '02 1: 40; Apr '02 2: 40; Apr '02 3: 40; Apr '02 4: 40; May '02 1: 40; May '02 2: 40; May '02 3: 40; May '02 4: 40; May '02 5: 40; Jun '02 1: 40; Jun '02 2: 40; Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40 | 0 | 600 | 600 |  |  |  |  | 0 |  |  |  |  | 600
Stress Test Lead | 9 | Feb '02 2: 40; Feb '02 3: 40; Feb '02 4: 40; Mar '02 1: 40; Jul '02 3: 40; Jul '02 4: 40; Aug '02 1: 40; Aug '02 2: 40 | 0 | 320 | 320 |  | 0 |  |  |  |  | 320
[48 empty] | 0 | 0
Project Manager | 10 |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [9 empty] | 40 | 1320 | 1360 | 40 |  |  |  |  | 1320
Project Assistant | 7 |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [10 empty] | 40 | 1280
[48 empty] | 0 | 0
Creative Director | 10 |  |  |  | 24 | 24 | 24 | 24 | 40 | 40 | 40 | 40 | 40 | 32 | 32 | 32 | 32 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [9 empty] | 24 | 672 | 696 | 24 |  |  |  |  | 672
Solution Architect | 9 |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [9 empty] | 40 | 1320 | 1360 |  | 40 |  |  |  |  | 1320
System Admin | 6 | [6 empty] | 40 | 40 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [9 empty] | 0 | 312
SO System Admin | 6 | Jun '02 3: 40; Jun '02 4: 40; Jul '02 1: 40; Jul '02 2: 40 | 0 | 160 | 160 |  |  |  |  | 0 |  |  |  |  | 160
Technical SMEs | 10 |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [9 empty] | 8 | 264 | 272 | 8 |  |  |  |  | 264
[48 empty] | 280 | 26416 | 26696 | 72 | 80 | 88 | 0 | 0 | 2416 | 3000 | 5160 | 7688 | 6560
[48 empty] | 240 | 24824 | 25064
[50 empty] | band 10 | 72 | 2416 | <===
[50 empty] | 9 | 80 | 3000 | <===
[50 empty] | 8 | 88 | 5160 | <=== Copy into IBM Pricing Model (Input Tab)
[50 empty] | 7 | 0 | 7688 | <===
[50 empty] | 6 | 0 | 6560 | <===
[51 empty] | 240 | 24824
[51 empty] | 2001 Rate |  |  |  |  | 2002 Rate
[52 empty] | 2001 Cost |  |  |  |  | 2002 Cost
[51 empty] | 335 | 24120 |  |  |  | 351.75 | 849828
[51 empty] | 250 | 20000 |  |  |  | 262.5 | 787500
[51 empty] | 220 | 19360 |  |  |  | 231 | 1191960
[51 empty] | 158 | 0 |  |  |  | 165.9 | 1275439.2
[51 empty] | 125 | 0 |  |  |  | 131.25 | 861000
[51 empty] | Total | 5029207.2
[51 empty] | Blended Rate |  | 188.388

## Assumptions
total hours
Number of Templates | 50
use case hours per template | 2 | 100
cm spec hours per template | 2 | 100
design hours per template | 12 | 600
cut/tag hours per template | 8 | 400
html hours per template | 2.6667 | 133.335
bones only cm impl per template | 4 | 200
final cm impl per template | 4 | 200
application design / deve

## Questions
No. | Category | Question | Work Product | Answer

## Work Products
Work Product | Category | Est. Hours | Resource
System Context | Arch | 40 | Sol Arch, KCM Arch
Component Model | Arch | 40 | Sol Arch, KCM Arch
Operational Models | Arch | 40 | Infra. Arch
Architectural Decisions | Arch | LOE | Sol Arch
Use Cases | Arch |  |  | Should be a factor times number of cases
Content Migration Strategy | Arch | 120 | Sol Arch, KCM Arch
Content Migration Code