IBM Global Services Proposal

for

Institutional XPress Design

Prepared for

New York Stock Exchange

11 Wall Street

New York, NY 10005

January 28, 2000

The information in this proposal shall not be disclosed outside of NYSE and shall not be duplicated, used or disclosed in whole or in part for any purpose other than to evaluate the proposal, provided that if a contract is awarded to IBM as a result of or in connection with the submission of this proposal, NYSE shall have the right to duplicate, use or disclose the information to the extent provided by the contract. This restriction does not limit the right of NYSE to use the information contained in the proposal if it is obtained from another source without restriction.

This proposal is valid until February 28, 2000 unless otherwise extended in writing by IBM.

IBM Global Services

- Executive Overview

The Internet and e-business have emerged as key strategic weapons for companies competing in the global marketplace. Many organizations are expanding, if not re-purposing their mission, to extend their reach and value by employing these versatile new business tools.    However, there is a significant amount of misuse of these technologies and distribution channels.  Critical to a successful implementation is the business strategy and planning to support these applications.

NYSE and  IBM have completed a Joint Requirements Definition (JRD) to analyze and understand NYSE’s business environment, strategies and objectives in order to determine how interactive tools and technologies can be applied effectively to NYSE’s business.

This document is a Statement of Work (SOW) to assist NYSE with the implementation of  the e-business mission.

- IBM Statement of Work for Institutional XPress Design

This Statement of Work (SOW), which includes the Appendices listed below, the Reference Agreement #JESC006 and any applicable attachments, will govern the Services specified in this Statement of Work.  In the event of conflict between the terms of this Statement of Work and the Reference Agreement #JESC006, the terms of this Statement of Work shall prevail.  This Statement of Work and the Reference Agreement #JESC006 (and any applicable attachments), represent the complete agreement regarding this subject matter and replace any prior oral or written communications between us.

The following Appendices are incorporated as part of this Statement of Work.

- Appendix A - Deliverable Materials Guidelines

- Appendix B - Project Change Control Procedure

- Appendix C - High Level Requirements Document

- Appendix D - Approval Process for Project Deliverables

- Appendix E - Signature Page

Changes to this Statement of Work will be processed in accordance with the procedure described in Appendix B - Project Change Control Procedure.  The investigation and implementation of changes may result in modification to the estimated schedule, charges, and/or other terms of the agreement.

2.1 Project Scope

The scope of this project is:

- To create and develop an Information Design that addresses the navigational flow and functional requirements as outlined in Appendix C - High Level Requirements Document.

- To create and develop a Creative Design that leverages the existing NYSE.com brand, and is consistent with the navigational flow and functional requirements as outlined in Appendix C - High Level Requirements Document.

- To prepare the Prototype HTML Framework for the Institutional XPress Web site as outlined in Appendix C - High Level Requirements Document.

- To create an Institutional XPress graphical Style Guide.

2.2 Key Assumptions

This Statement of Work with its estimated schedule and charges are based on the following key assumptions.  Deviations from these assumptions may result in changes to the tasks, schedule and charges.  Changes that arise during the proposed project will be managed through the procedure described in Appendix B - Project Change Control Procedure.

General Assumptions

    - Work under this SOW will be performed at the IBM location in Atlanta, Georgia or in New York, New York or in other Centers for IBM e-business Innovation as necessary.

    - The actual period of performance will be determined at the time work is authorized under this SOW, based upon schedule and availability of resources.

    - IBM will provide services under this SOW during normal business hours, 8:00 AM – 5:00 PM, Monday through Friday, except holidays.

    - Some IBM tasks in this SOW may be performed by IBM subcontractors.

    - Any activity not explicitly defined in this SOW will be treated as a project change and will be processed in accordance with the procedure described in Appendix B - Project Change Control Procedure. Work on any requested project modifications will not begin without approval of a cost and schedule change via a Project Change Request.

    - IBM assumes that Appendix C - High Level Requirements Document is approved by NYSE.

    - NYSE personnel who will be assigned to this project will have the technical skills necessary to participate in this project.

    - IS and user personnel will be available as described in NYSE responsibilities and key assumptions.

    - NYSE will be charged for travel time that exceeds one hour round trip from the point of departure.

    - Browser compatibility will only consist of Internet Explorer 4.0 and later and Netscape 4.5 and later running on 32-bit Windows operating systems.

    - IBM is not responsible for managing Third-party work and/or deliverables unless explicitly contracted to do so under this SOW or through a PCR.

    - All content is in US English, and no multi-lingual requirements exist for this effort.

    - Services for Web Hosting are not included in this SOW.  IBM would be pleased to respond to NYSE for the addition of these services.

    - Services for Security are not included in this SOW.  IBM would be pleased to respond to NYSE for the addition of these services.

    - Streaming audio and/or video creation, configuration, or hosting are not within the scope of this SOW.

    - Search functionality is not within the scope of this SOW.

    - eCommerce functionality is not within the scope of this SOW.

    - Stress-testing is not within the scope of this SOW.

    - Y2K services are not within the scope of this SOW.

NYSE Assumptions

- NYSE understands that completion of the work described in this SOW is based on a strict schedule.  NYSE agrees that failure to meet milestones in this schedule may cause future deliverable dates to change.

- NYSE will assume all responsibilities for the copyright clearance, license, and usage agreements for any and all content and/or graphical assets used on or loaded to the Institutional XPress system.

- NYSE personnel assigned to this project will possess the appropriate business expertise, technical skills, and can devote sufficient time as necessary to complete the development effort in accordance with the schedule.

- NYSE will appoint a single project liaison with sufficient expertise, availability, and authority to answer questions, resolve issues, and communicate project-related decisions to IBM.  Questions may include, but are not limited to, business process or logic, data, content, connectivity, or existing information technology.

- NYSE liaison or their designee will respond to written questions and issues within three (3) business days.  The liaison's answer is considered final and subsequent modifications will be processed in accordance with the procedure described in Appendix B.

- NYSE will provide IBM a list and count of all assets sent to IBM.

- NYSE is responsible for all URL registration (where applicable).

- NYSE is responsible for SSL Certificates (where applicable).

- NYSE will provide a copy of their current application, for reference use only, to IBM prior to commencement of the Information Design task.

- NYSE assumes all responsibility for installation and maintenance of Lotus Notes, browsers, and other software on all NYSE workstations or internal Institutional XPress systems.

- HTML templates will be developed and maintained through the use of a standard HTML editor as per the NYSE standard.

- NYSE is responsible for developing the Application defined by the deliverables in this SOW.

Creative Assumptions

    - All photos, logos, and other graphic assets will be provided before the start of design production.

    - Institutional XPress Graphical User Interface will be designed to meet a minimum of 800X600 pixels.

    - Design Studies will be optimized for the Web color palette.

    - Browser compatibility will only consist of Internet Explorer 4.0 and later and Netscape 4.5 and later running on 32-bit Windows operating systems.

    - Design implementation occurs after information design is completed and approved by the client. Information design consists of  flow of site and functional templates. Any information design changes after that time will impact schedule and budget, and will be processed in accordance with the procedure described in Appendix B.

    - Editorial services, other than proofreading and quality control, are not within the scope of this SOW.

    - Rework of editorial content is not within the scope of this SOW.

    - Any content provided by client will be presented in either Microsoft Word (.doc) or Rich Text  Format (RTF).

    - Focus groups and usability testing are highly recommended, but are not within the scope of this SOW.

    - High-Level information design and flow charts will be approved before functional templates are created.

    - Due to time constraints, NYSE will accept one (1) revision cycle of Information Design and Creative Design deliverables. NYSE and IBM will discuss and document revisions to be made, IBM will make revisions, and deliverable will be considered final. Additional revision cycles will be treated as a project change and will be processed in accordance with the procedure described in Appendix B - Project Change Control Procedure.

    - Prototype HTML Framework will consist of example-only HTML for NYSE reference and will include one (1) example of each approved screen design. Production HTML is the responsibility of NYSE.

2.3 IBM Responsibilities

- Under this Statement of Work, IBM will perform the following activities:

2.3.1 Project Management

- Description:

- The purpose of this activity is to provide direction and control of IBM project personnel and to provide a framework for project planning, communications, reporting, procedural and contractual activity.  IBM will perform the following tasks:

- 	Review project goals and objectives, the Statement of Work and the contractual responsibilities of both  parties with the NYSE Project Manager.

- 	Review areas of risk and containment plans with the NYSE Project Manager.

- 	Maintain project communications through the NYSE Project Manager.

- 	Establish documentation and procedural standards for project deliverables.

- 	Prepare a Project Plan for performance of this Statement of Work which outlines the tasks, milestones and estimated schedule.

- 	Measure and evaluate progress against the Project Plan with the NYSE Project Manager.

- 	Resolve deviations from the Project Plan.

- 	Conduct regularly scheduled project status meetings.

- 	Prepare and submit a Status Report weekly to the NYSE Project Manager.

- 	Administer the Project Change Control Procedure with the NYSE Project Manager.

- 	Coordinate and manage the activities of project personnel.

- Completion Criteria:

- This activity will be complete when the IBM tasks described in this section have been completed, according to their completion criteria, or IBM has met the criteria defined in Section 2.7 “Completion Criteria” of this Statement of Work.

- Deliverables:

- Weekly Status Reports

- Project Plan

2.3.2 Create Information Design

- Description:

- The purpose of this activity is to provide a Detailed Navigational Flow Chart depicting navigational flow and to provide a set of Functional Templates (1 page per template) that define the general location and function of major  screen elements for each screen defined within the Detailed Navigational Flow Chart.

- Completion Criteria:

- This task will be complete upon delivery of the Detailed Navigational Flow Chart and the Functional Templates (1 page per template) to the NYSE  Project Manager in accordance with the approval process described in Appendix D - Approval Process for Project Deliverables.

- Deliverables:

- Detailed Navigational Flow Chart

- Functional Templates

2.3.3 Create Design Study

- Description:

- The purpose of this activity is to provide a Creative Design Study for Institutional XPress that leverages the existing NYSE.com brand.

- Completion Criteria:

- This task will be complete upon delivery of the Design Study to the NYSE Project Manager in accordance with the approval process described in Appendix D - Approval Process for Project Deliverables.

- Deliverables:

- Design Study

2.3.4 Create Graphic Elements

- Description:

- The purpose of this activity is to create the Graphic Elements consistent with the approved Design Study for Institutional XPress.

- Completion Criteria:

- This activity will be complete when the IBM tasks described in this section have been completed, according to their completion criteria, or IBM has met the criteria defined in Section 2.7 “Completion Criteria” of this Statement of Work.

- Deliverables:

- None – These Graphic Elements will be delivered as part of the Prototype HTML Framework deliverable.

2.3.5 Create Prototype HTML Framework

- Description:

- The purpose of this activity is to prepare the Prototype HTML Framework for the Institutional XPress Web site.  This task consists of the following subtasks:

- Develop the HTML code with applicable links that incorporate the design of the Institutional XPress site as defined in this SOW.

- Conduct a detail design review of the resultant HTML prototype with the NYSE Project Manager.

- Completion Criteria:

- This task will be complete upon delivery of the Prototype HTML Framework to the NYSE  Project Manager in accordance with the approval process described in Appendix D - Approval Process for Project Deliverables.

- Deliverables:

- Prototype HTML Framework code.

2.3.6 Create Institutional XPress Style Guide and Supporting Files

- Description:

- The purpose of this activity is to provide a Style Guide document and Supporting Files.  The Style Guide will define the graphic standards that have been established for the Institutional XPress application. The Supporting Files provide the templates, palettes and global graphical assets necessary to create additional application screens.

- Completion Criteria:

- This task will be complete upon delivery of the Style Guide document and Supporting Files to the NYSE Project Manager in accordance with the approval process described in Appendix D - Approval Process for Project Deliverables.

- Deliverables:

- Style Guide and Supporting Files

2.4 NYSE Responsibilities

- The  successful  completion of the proposed effort depends on the full commitment and participation of NYSE management and personnel.

- The responsibilities listed in this section are in addition to those responsibilities specified in the Reference Agreement #JESC006and are to be provided at no charge to IBM.  IBM's performance is predicated upon the following responsibilities being fulfilled by  NYSE.

2.4.1 NYSE Project Manager

- Prior to the start of this Statement of Work, NYSE will designate a person called the NYSE Project Manager who will be the focal point for all IBM communications relative to this project and will have the authority to act on behalf of NYSE in matters regarding this project.  The NYSE Project Manager's responsibilities include the following:

- 	Serve as the interface between IBM and all NYSE departments participating in the Project.

- 	Administer Project Change Control along with the IBM Project Manager.

- 	Attend project meetings.

- 	Obtain and provide information, data, decisions and approvals within three (3) working days of IBM's request unless NYSE and IBM agree in writing to a different response time.

- 	Provide approvals of deliverables per the approval process described in Appendix D - Approval Process for Project Deliverables.

- 	Resolve deviations from Project Plans, which may be caused by NYSE.

- 	Help resolve project issues and escalate issues within NYSE, as necessary.

- 	Schedule and secure attendance of all required NYSE personnel as required for interviews, meetings , work sessions and telephone conversations.

- 	Provide access to relevant NYSE information and documents required for the project.

2.4.2 Copyright Clearance and Usage Agreements

- NYSE assumes responsibility for all electronic copyright clearance and usage agreements for any and all content to be included in the Prototype HTML Framework Code or other Deliverables, as applicable.

2.4.3 Required Consents

- NYSE will promptly obtain and  provide to IBM all Required Consents necessary for IBM to provide the Services described in this Statement of Work.  A Required Consent means any consents or approvals required to give IBM and IBM subcontractors the right or license to access, use and/or modify (including creating derivative works) the hardware, software, firmware and other products that NYSE uses or will use, without infringing the ownership or license rights (including patent and copyright) of the providers or owners of such products.

- NYSE will indemnify, defend and hold IBM, IBM affiliates and subcontractors, harmless from and  against any and all claims, losses, liabilities and damages (including reasonable attorneys' fees and costs) arising from or in connection with any claims (including patent and copyright infringement) made against IBM, alleged to have occurred as a result of NYSE’s failure to provide any Required Consents.

- IBM will be relieved of the performance of any obligations that may be affected by NYSE’s failure to promptly obtain and provide any Required Consents to IBM.

2.4.4 Laws, Regulations, and Statutes

- NYSE is responsible for the identification and interpretation of any applicable laws, regulations, and statutes that affect the NYSE applications to which IBM will have access during this project.  It is the responsibility of NYSE to ensure that the applications meet the requirements of those laws, regulations and statutes.

2.4.5 Data Security

- NYSE is responsible for the actual content of any data file, selection and implementation of controls on its access and use, and security of the stored data.

2.5 Deliverable Materials

- The following are classified as Type II Materials, as defined in the Reference Agreement #JESC006 and will be delivered to NYSE under this Statement of Work:

- Weekly Status Reports

- Project Plan

- Detailed Navigational Flow Chart

- Functional Templates

- Design Study

- Prototype HTML Framework Code

- Style Guide and Supporting Files

- Type II Materials are those, created during the Service performance period or otherwise (such as those that preexist the Service), in which IBM or third parties have all right, title, and interest (including ownership of copyright).  IBM will deliver one copy of the specified Materials to NYSE.  IBM grants NYSE an irrevocable, nonexclusive, worldwide, paid-up license to use, execute, reproduce, display, perform, and distribute, within its Enterprise only, copies of Type II Materials.

2.6 Estimated Schedule

- The services in this Statement of Work are estimated to be performed over  the time period outlined in the Project Plan. The Project Plan will be revalidated and adjusted upon the acceptance of this SOW by NYSE.

2.7 Completion Criteria

- The project will be considered complete when any of the following first occurs:

- IBM accomplishes the IBM activities described in Section 2.3 “IBM Responsibilities” including delivery to NYSE of the materials listed in Section 2.5 “Deliverable Materials”.

- IBM provides the number of hours of services specified in Section 2.8 “Charges” or in any subsequent change authorization.

- NYSE or IBM terminates the project in accordance with the provisions of the Reference Agreement #JESC006.

2.8 Charges

- Our engagement will be conducted on a time and materials basis.

- IBM will provide up to a total number of <Number of hours> hours for this Service at an hourly rate of $<Hourly rate> per hour.   The estimated professional services charges for this Statement of Work are       $<Fee total> and are exclusive of any travel and living expenses and any applicable taxes.  In addition, two percent (2%) of the professional services charges will be billed as an administrative fee.

- NYSE will be billed actual travel and living costs currently estimated to not exceed  <Travel fee estimate>

- The hours specified above are IBM's estimate based upon the information available at this time.  We will notify NYSE as soon as practical of any changes in our estimates.

- IBM will invoice NYSE monthly.

2.9 Year 2000

- IBM is not providing any Year 2000 services under this Statement of Work.  IBM Product Specifications specify the Year 2000 readiness of the IBM Products.  IBM does not make any representations regarding the Year 2000 readiness of the non-IBM Products.

- Under the terms of this Statement of Work IBM is not responsible for 1) NYSE products, 2) a third party's products (including products NYSE licenses from IBM's subcontractors) 3) IBM's previously installed Products, or 4) "Other Products" to correctly process or properly exchange accurate date data with the Products or deliverables IBM provides.  IBM will be relieved of  its obligations under this Statement of Work due to the inability of such Other Products to correctly process or properly exchange accurate date data with the Products or deliverables we provide to NYSE.  NYSE acknowledges that it is NYSE’s responsibility to assess its current systems and take appropriate action to migrate to Year 2000 ready systems.

2.10 Security Disclaimer

- IBM is not providing any Security services under this Statement of Work.  IBM has offered NYSE security services for the Institutional XPress Design project.  NYSE has chosen not to have security as part of the Institutional XPress Design project.  As such, IBM does not make any representations regarding, and NYSE assumes all responsibility for, the Security readiness, or lack of readiness, of the deliverable(s).

- The Services performed by IBM will be performed using reasonable care and skill.  New technology, configuration changes, software upgrades and routine maintenance, among other items, can create new and unknown security exposures.  Computer “hackers” and other third parties continue to employ increasingly sophisticated techniques and tools, resulting in ever-growing challenges to individual computer system security.  It is your sole responsibility to maintain the security of your computer systems and the data contained in them.  Our performance of Services, including any recommendations made, does not constitute any representation or warranty by us about the security of your computer systems including, but not limited to, any representation that your computer systems are safe from intrusions or an other security exposures.

- Other than the warranty for IBM services set forth in the Agreement, we provide no other warranties, whether express or implied, in connection with any services or deliverables under this Statement of Work, and that all other warranties, including, without limitation, the implied warranty of merchantability and fitness for particular purpose are expressly disclaimed.

Appendix A - 	Deliverable Materials Guidelines

- A.1  Weekly Status Report

The one (1) to three (3) page Weekly Status Report will consist of the following, as appropriate:

- Planned hours vs. actual hours used to date.

- Activities performed during the reporting period.

- Activities planned for the next reporting period.

- Project Change Control summary.

- Problems, concerns and recommendations.

- Other items of Importance.

- A.2  Project Plan

The one (1) to three (3) page Project Plan will consist of the following, as appropriate:

- Activities planned - high level description of major tasks and milestones with identification of appropriate deliverables and planned review cycle.

- Estimated Schedule for each high level task with associated milestones and deliverables.

- A.3  Detailed Navigational Flow Chart

IBM will provide a one (1) page Detailed Navigational Flow Chart depicting navigational flow of the Institutional XPress Web Site.

A.4  Functional Templates

IBM will provide one (1) set of Functional Templates (1 page per template), up to eight (8) pages,  that define the general location and function of major  screen elements for each screen defined within the Detailed Navigational Flow Chart.

A.5  Design Study

IBM will provide one (1) Design Study for each of two (2) pages: Home Page and “next level” page. The “next level” page will be a representative creative design to be implemented for the pages throughout the Web Site that follow the Home Page. The Design Study will demonstrate the stylistic impression created to give a proposed visual representation of how the Web site should look and feel. The proposed Design Study will take the form of color prints of pages created in a graphics design software application.

A.6  Prototype HTML Framework Code

The Prototype HTML Framework Code will consist of the applicable HTML code and Graphic Elements with applicable links that incorporate the creative and information design of the Institutional XPress Web Site as described in this SOW.

A.7  Style Guide and Supporting Files

IBM will provide a five (5) to ten (10) page Style Guide document which will define the graphic standards that have been established for the Institutional XPress application. Additionally, IBM will provide up to six (6) electronic Supporting Files for the templates, palettes and global graphical assets necessary to create additional application screens.

Appendix B - 	Project Change Control Procedure

- Changes to Services described in this Statement of Work, including addition and deletion of Services, will be submitted  in a Project Change Request (PCR). The PCR will describe the change, the rationale for the change, and the effect the change will have on the Statement of Work.  The designated Project Manager of the requesting party must authorize the request before submission to the other party. The receiving party may either accept the PCR for implementation or further investigation, or reject it. Before we start our investigation, IBM will inform NYSE of any additional charges to investigate a PCR that you authorize.  If accepted for implementation, the PCR or a Change Authorization will be signed by both parties authorizing the change.

- Any change in the Statement of Work may affect the charges, estimated schedule, or other terms.

Appendix C - 	High Level Requirements Document

- <add copy of High Level Requirements Doc>

Appendix D - 	Approval Process for Project Deliverables

- IBM and NYSE acknowledge that one of the keys to success in this project is a working relationship that respects the strengths, abilities, and responsibilities of each company.  The approval process for materials delivered by this work should fundamentally focus attention on whether or not we are jointly meeting the overall requirements of NYSE.  Therefore, for each formal deliverable from IBM which requires NYSE approval under this Statement of Work, the process will be:

- The IBM Project Manager will deliver the materials to NYSE Project Manager.

- NYSE Project Manager will arrange for the proper personnel in the NYSE organization to review the materials.  He/she will then consolidate all feedback in written form back to IBM’s Project Manager.

- The feedback should contain either a letter of approval or a letter of disapproval.  In the case of disapproval, the feedback should describe the specific instances where the material does not meet the NYSE requirements.  For each instance of disapproval, NYSE must specify the criteria required to gain approval.

- The feedback to IBM should be complete within three (3) business days of receiving the materials.

- The IBM Project Manager will specify the plans to correct each disapproval instance in writing to NYSE.

- IBM will make corrections to the deliverables to NYSE approval criteria.  If, in the judgment of either IBM’s or NYSE’s Project Manager, the changes required are beyond the scope of the original Statement of Work or extensive enough to warrant, the changes will be handled using the Project Change Control Procedure outlined in Appendix B.

Appendix E – Signature Page

An authorized signature on the following page by NYSE indicates your acceptance of this Statement of Work.

Customer Agreement

Statement of Work for Services

Custom Services

Scope of Services, responsibilities, completion criteria, charges, and other applicable terms:

Refer to the IBM Statement of Work for Institutional XPress Design dated January 28, 2000.

Each of us agrees that the complete agreement between us about these Services consists of  1) this Statement of Work and 2) the Reference Agreement #JESC006.

| Agreed to: |  |  | Agreed to: |  |
| --- | --- | --- | --- | --- |
| NYSE |  |  | International Business Machines Corporation |  |
|  |  |  | Armonk, New York 10504 |  |
| By: |  |  | By: |  |
| Authorized signature |  |  | Authorized signature |  |
| Name (type or print): |  |  | Name (type or print): |  |
| Date: |  |  | Date: |  |
| Customer number: |  |  | Reference Agreement number: JESC006 |  |
|  |  |  | Statement of Work number: |  |
| Customer address: |  |  |  |  |
| <Address 1> |  |  | IBM Office Address: |  |
| <Address 2> |  |  | Business Type: |  |
|  |  |  | Offering Code: |  |
| Project Name: | Institutional XPress Design |  |  |  |