Carnegie Mellon University	 CMU-MSIT-SE

School of Computer Science	Fall 2003

Master of Software Engineering

MSIT-SE Practicum

Software Project Management Plan:

Railroad Configuration Rule Checker

September 26, 2003

Yong Hoon Choi

Revision History

| Date | Revision | Description | Author |
| --- | --- | --- | --- |
| 09/26/2003 | 1.0 | Documentation Creation | Yong Hoon Choi |
| 09/29/2003 | 1.1 | Modification from Mentor Review |  |

Table of Contents

1	Introduction	4

2	Overview	5

2.1	Project summary	5

2.1.1	Purpose, scope, and objectives	5

2.1.2	Assumptions and constraints	6

2.1.3	Project deliverables	6

2.1.4	Schedule	7

2.1.5	Evolution of the SPMP	7

3	Reference	8

4	Definitions, Acronyms and Abbreviations	9

5	Project organization	10

5.1	External interface	10

5.2	Internal structure	10

5.3	Roles and responsibilities	10

6	Managerial process plans	11

6.1	Management objectives	11

6.2	Project start-up plan	11

6.2.1	Estimation plan	11

6.2.2	Staffing plan	11

6.2.3	Resource acquisition plan	11

6.2.4	Project staff training plan	11

6.3	Work plan	11

6.3.1	Work activities & schedule allocation	11

6.4	Control plan	12

6.4.1	Requirements control plan	12

6.4.2	Schedule control plan	13

6.4.3	Quality control plan	13

6.4.4	Reporting plan	13

6.4.5	Metrics collection plan	13

6.5	Risk management plan	13

6.6	Project closeout plan	14

7	Technical process plans	15

7.1	Process model	15

7.2	Methods, tools, and techniques	16

7.3	Infrastructure plan	16

7.4	Product acceptance plan	16

8	Supporting process plans	17

8.1	Configuration management plan	17

8.2	Verification and validation plan	17

8.3	Documentation plan	17

# Introduction

The Software Project Management Plan (SPMP) for the Railroad Configuration Rule Checker project is the controlling document for managing the software project; it defines the technical and managerial processes necessary to develop software work products that satisfy the product requirements.

Infrastructure components of a railroad consist of various types of devices that are used to facilitate the movement of trains, and the configuration of a railroad is very dynamic, i.e., the layout and positioning of the devise is constantly changing. This required the CAD software to be designed so that the configuration changes could be imported without having to make changes to the logic whenever a component was updated. The procedural method for updating the configuration is for a technician to manually edit the tabling files, making changes to the component parameters based on information supplied from the railroad. There are possibly a variety of different rules that the technician must understand and adhere to in order to deliver tabling that is free of defects. A violated rule, however, will still allow the software to be compiled and linked without error as long as the macro is syntactically correct, so the build process allows no ability to detect tabling defects. The railroad configuration rule checker would examine the updated tabling file in order to ensure that the tabling updates comply with all the rules, and to inform the user when an error is detected.

This software development project is one of the degree requirements for the Master of Science, Information Technology – Software Engineering (MSIT-SE) program at Carnegie Mellon University.

# Overview

## Project summary

### Purpose, scope, and objectives

The purpose of the project is to deliver the Railroad Configuration Rule Checker application satisfying the client’s requirements. The SPMP will cover the major tasks, resources, schedules for developing the Railroad Configuration Rule Checker application.

The objectives of the practicum are as follows:

- To use software engineering to a real world problem

  - Apply knowledge and techniques leaned in the courses of the MSIT-SE program as in the table below.

| Core Course | Project Activities |
| --- | --- |
| Models of Software Systems | - Formal Modeling & Specification for Configurations and Rules - Model Checking and Satisfiability Problem Solving |
| Managing Software Development | - Software Project Management Plan - Task/Risk Analysis |
| Methods of Software Development | - Problem Frames: Analyzing and Structuring Software Development Problems - Usability Analysis using Cognitive Walkthrough |
| Analysis of Software Artifact | - Software Performance/Behavior Analysis - Software Testing |
| Architecture of Software Systems | - Quality Attribute Analysis in Software Architecture - Modeling Using Acme ADL and AcmeStudio |

  - Try to learn new concepts and experience new ways of doing things

  - Survey and compare alternative techniques applied to the problem using systematic approaches

- To deliver a quality software product

  - Set realistic goals

  - Meet deadlines

  - Deliver quality documentations that meets the client’s expectation as well as the industry standards

  - Communicate openly with the client and mentor in a timely manner

- To expand technical knowledge

  - Learn from the CMU mentor and the technical staffs at Union Switch & Signal, Inc.

  - Understand the Computer Aided Dispatch (CAD) software systems and the related processes in the railroad industry

  - Understand verification (rule checking) techniques applied to the configuration/design problems.

### Assumptions and constraints

The following constraints and assumptions will be imposed on the project during the whole duration of the project.

- The project will follow a personal software process.

- The project duration will be restricted to the fall semester of 2003 in the Carnegie Mellon University academic calendar.

- No budget or cost management is required in regards to resource and personnel purchasing, upkeep and retaining.

- The primary computing resources will be the computing lab (Wean Hall 4615), provided by the Institute for Software Research, International (ISRI).

- The development time on the project will be limited to approximately 24 hours per week.

### Project deliverables

#### Document deliverables

##### Documents for CMU

The following documents will be delivered to CMU and/or used for the quality software development:

- Practicum Proposal

- Software Requirement Specification (SRS)

- Software Project Management Plan (SPMP)

- Software Configuration Management Plan (SCMP)

- Software Design Document (SDD)

- Software Testing Document (STD).

##### Documents for Client

The following documents will be provided to the client:

- Practicum Proposal

- Software Requirement Specification

- Software Design Document (SDD)

- Users’ Manual.

#### Software Deliverable

The railroad configuration rule checker software system complying with the Software Requirement Specification (SRS) document will be delivered.

#### Presentation

The final presentation will be given to the MSIT-SE practicum audience at the last phase of the project.

### Schedule

| TimeLine | Activities | Deliverables |
| --- | --- | --- |
| Friday, September 19, 2003 | Project start | Proposal |
| Friday, September 28, 2003 | Planning | SPMP |
| Friday, October 3, 2003 | Requirement Analysis | SRS |
| Friday, October 10 2003 | Model & Specification of Problem | Progress Report |
| Friday, October 17, 2003 | Software Architecture Design | Progress Report |
| Friday, October 24, 2003 | Detailed Design | Progress Report |
| Friday, October 31, 2003 | GUI Design | SDD |
| Friday, November 28, 2003 | Implementation | Executable Code |
| Friday, December 5, 2003 | User Manual, Testing Document | STD |
| Friday, December 12, 2003 | Project Completion | Presentation |

### Evolution of the SPMP

The software project management plan is under version control. Proposed changes and new versions of the plan are announced on the practicum website (http://www.cs.cmu.edu/~yhchoi/practicum.htm) and are made available to interested stakeholders.

# Reference

- IEEE Std 1058-1998, “IEEE Standard for Software Project Management Plans”, IEEE 1998

- Chris F. Kemerer, “Software Project Management Readings and Cases”, Irwin, 1997

- Watts S. Humphrey, “Introduction to the Personal Software Process”, Addison Wesley, 1997

# Definitions, Acronyms and Abbreviations

All acronyms, abbreviations, and the technical terms used in this document are arranged in alphabetical order.

| CAD | Computer Automated Dispatch |
| --- | --- |
| CMU | Carnegie Mellon University |
| ISRI | Institute for Software Research, International |
| MSE | Master of Software Engineering |
| MSIT-SE | Master Science in Information Technology – Software Engineering |
| SCMP | Software Configuration Management Plan |
| SDD | Software Design Document |
| SEI | Software Engineering Institute |
| SPMP | Software Project Management Plan |
| SRS | Software Requirement Specification |

# Project organization

## External interface

The client for this project is Union Switch & Signal, Inc, System Engineering Group, represented by Gregg Beardsley and Greg Matoka. The communication is done via e-mail on “as need basis” and through regular meetings with client.

## Internal structure

Since the project will be performed by an MSIT-SE student, there is no internal structure of the project organization. The student will get advice from Dave Root (CMU mentor), Greg Matoka (technical advisor), and Gregg Beardsley (Supervisor).

## Roles and responsibilities

| Role | Responsibilities |
| --- | --- |
| Software Engineer | - Build up management plans - Track process against the plan - Obtain resources necessary for the project - Report progress and issues to mentors - Maintain the practicum web-site - Actively communicate with the client and the mentor |
| Supervisor | - Provide managerial guidelines - Providing necessary support and supervision |
| Technical Advisor | - Provide technical input on all project reviews and activities - Providing necessary support and supervision |
| CMU Mentor | - Advise the knowledge/methodology applied to the practicum project - Advise the quality of deliverables |

# Managerial process plans

This section will describe the project management processes for the project including the project start plan, risk management plan, project work plan, project control plan and project closeout plan.

## Management objectives

The primary objective of the project management is to ensure the successful completion of the project. As a result, the project will deliver a quality product, which satisfies the needs of the client outlined in the SRS, to the client on time.

## Project start-up plan

The start-up plan shall specify the estimation plan, staffing plan, resource acquisition plan, and training plan.

### Estimation plan

As soon as the high-level software design is developed and the system is decomposed into subsystems/modules the estimation plan will be prepared as part of the SPMP.

### Staffing plan

This project will be performed by a fixed staff consisting of one MSIT-SE student.

### Resource acquisition plan

All the resources from the MSIT-SE program are available to the project. Any necessary software might be obtained with the help of the MSE Studio toolsmith. All administrative assistance could be obtained by contacting to Ellen Saxon. The final presentation rehearsal advice could be obtained from Linda Hutz Pesante at SEI. For other resources for the final presentation, the project staff could contact to Linda Smith.

### Project staff training plan

There is no explicitly defined staff training plan for the project. The staff, however, will try to survey on the following areas:

- Modeling and specification techniques for the railroad configuration

- Formal language specification for the configuration rules

- Verification techniques for the configuration rule checking.

## Work plan

This section shall specify the work activities, schedule, and resources for the software project.

### Work activities & schedule allocation

The overall project plan for the project is given in the table below.

| ID | Task name |  |  | Start date | Finish date |
| --- | --- | --- | --- | --- | --- |
|  | Project initiation |  |  | 09/08/03 | 09/19/03 |
|  |  | Conception exploration |  | 09/08/03 | 09/12/03 |
|  |  | Proposal |  | 09/15/03 | 09/19/03 |
|  | Management planning |  |  | 09/22/03 | 09/28/03 |
|  | Requirement |  |  | 09/29/03 | 10/03/03 |
|  |  | Requirement gathering/analysis |  |  |  |
|  |  | Requirement documentation |  |  |  |
|  | Modeling & specification for problem space |  |  | 10/06/03 | 10/10/03 |
|  |  | Modeling for the railroad configuration |  |  |  |
|  |  | Specification for configuration rules |  |  |  |
|  |  | Rule checking scheme development |  |  |  |
|  | Software Design |  |  |  |  |
|  |  | Software architecture design |  | 10/13/03 | 10/17/03 |
|  |  |  | Quality attributes analysis |  |  |
|  |  |  | Candidate architecture build-up |  |  |
|  |  |  | Architecture analysis |  |  |
|  |  |  | Final architecture description |  |  |
|  |  | Low-level design |  | 10/20/03 | 10/24/03 |
|  |  | Graphic User Interface design |  | 19/27/03 | 10/31/03 |
|  |  |  | Prototype design |  |  |
|  |  |  | Usability analysis |  |  |
|  |  |  | Review/update GUI design |  |  |
|  | Implementation |  |  | 11/03/03 | 11/28/03 |
|  |  | Prototype implementation |  |  |  |
|  |  | Final Product implementation |  |  |  |
|  | Verification & Validation |  |  | 12/01/03 | 12/05/03 |
|  |  | Prototype testing |  |  |  |
|  |  | Final testing |  |  |  |
|  | User Documentation |  |  | 12/01/03 | 12/05/03 |
|  | Final Presentation |  |  | 12/08/03 | 12/12/03 |

## Control plan

This section will describe the metrics, reporting mechanisms, and control procedures necessary to measure report and control the product requirements, the project schedule, resources and quality of work processes and work products.

### Requirements control plan

The Software Requirement Specification (SRS) will be the formal document for all requirements in the project. All changes after the formal release of the SRS will be documented according to the Software Configuration Management Plan (SCMP).

### Schedule control plan

The SPMP will contain the schedule plan for each cycle at the start of the cycle, which will include reasonable milestones based on the goals of each cycle. The project staff will record all time spent working on the project each week. Every two weeks the schedule will be reconsidered and re-planed to ensure that it is reasonable and the staff follows schedule. The project staff is responsible for informing the client and the CMU mentor of the updated schedule and status.

### Quality control plan

QA Plan

### Reporting plan

The progress status of the project will be reported to the CMU mentor and the technical advisor in a weekly meeting. Although formal reporting should take the form of face-to-face meetings with the client, if the client is not available, a written or electronic report will be sufficient. The final presentation for wrapping up the whole project will be given at the end of the semester.

### Metrics collection plan

The metrics collected on this project will be restricted to time spent, lines of code (LOC) developed converted, and defects discovered. Information on the LOC will include LOC in the product, LOC actually needed, and LOC converted. Time spent will be recorded and analyzed as mentioned in section 6.4.2, schedule control plan. Defects will be recorded and analyzed as described in the Quality Assurance plan.

## Risk management plan

Risks will be managed through a spreadsheet to be developed and maintained by the project staff. The spreadsheet will be available on the project web site (http://www.cs.cmu.edu/~yhchoi/practicum.htm). The top 5 risks will be reviewed and updated in a weekly basis.

#### Identify Risk

Throughout the project, the engineer will consider risks to the successful completion of the project and document those risks in the risk spreadsheet. The engineer will continuously consider the project in light of risk and any new risks that come up will be added to the risk spreadsheet.

#### Assess Risk

The engineer will assess and document the probability of the risk occurring and the severity of the effect on the project if the risk did occur. The rating for this assessment is as follows:

- Probability:

| High (H) | The risk is more likely to occur | >> 75% |
| --- | --- | --- |
| Medium High (MH) | The risk is likely to occur | > 50% |
| Medium Low (ML) | The risk is likely not to occur | < 50% |
| Low (L) | The risk is more likely not to occur | << 25% |

- Severity:

| High (H) | The risk, if unmitigated, would result in a complete failure for the project. |
| --- | --- |
| Medium High (MH) | The risk, if unmitigated, would have a major impact on the project’s schedule, cost, or performance. |
| Medium Low (ML) | The risk, if unmitigated, would have a certain impact on the project’s schedule, cost, or performance. |
| Low (L) | The risk, if unmitigated, would have a minor impact on the project. |

Based on the assessment of the risks, the new top 5 risks will be determined by prioritization of the list.

#### Analyze Risk

Based on the rating to each risk, risks will be analyzed to determine what action the project will take. That action could include immediate programmatic changes to ensure that the risk does not occur, development of mitigation plans that could be implemented in the event of the occurrence of the risk, or some other action as appropriate.

#### Monitor Risk

Every effort will be made to ensure that the risks do not occur, and if they do occur, that the engineer the occurrence of the risk as soon as possible. Early notice can limit any possible negative effects of the risks on the project. If progression of the project changes the assessment of the probability or/and severity of a risk, the risk will be analyzed and the risk spreadsheet will be updated.

#### Mitigate Risk

In the event that a risk does occur, the issue will be analyzed in light of the mitigation plans and action will be taken as appropriate.

## Project closeout plan

The project will end in December 2003. At that time, the project staff will provide the client a copy of all the documents in electronic format, conduct a project postmortem, and archive all the project artifacts including documents, source code, project plans, user documentation.

# Technical process plans

This section will specify the development process model, technical models, tools and techniques that will be used to develop the work products, project infrastructure and product acceptance plan.

## Process model

The project will follow an incremental waterfall development model and the simplified Personal Software Process 3 model. While the PSP3 process is mainly targeted for large-scale program developments, the project is expected to be relatively small and fast-paced in a short period. Therefore, the cyclic personal process is introduced but simplified. The development process model is illustrated in Figure 1. In addition, the process model basically consists of the following activities:

- Requirements analysis and definition     The system’s services, constraints and goals are established with system users. They are defined in detail and serve as a software requirement specification.

- System/software design     The system/software design process partitions the requirements to sub-systems. Software design involves identifying and describing the fundamental software system abstractions and their relationships.

- Implementation and unit testing     The software design is realized as a set of programs or program units. Unit testing involves verifying that each unit meets its specification.

- Integration and system testing     The individual program units or programs are integrated and tested as a whole system to ensure that the software requirements have been met. After testing, the software system is delivered to the client.

- Postmortem     The software system is installed and put into practical use. The project goals and data are reviewed for improving current processes.

Requirements

Analysis/Design

High-level

Design

High-level

Design Review

Cyclic

Development

Post-mortem

Specify Cycle

Detailed Design

/Reviews

Test Development

and Reviews

Implementation

and Code Reviews

Test

Reassess and Recycle

Figure 1. Modified Personal Software Process

## Methods, tools, and techniques

The formal modeling/specification techniques will be used for the configuration rule checking. A formal language should be defined appropriate for configuration rules (specification) written in a natural language (English). Model Checking could be a good candidate technique for verification since it is totally automatic and provides counter-examples when it gets a negative result. If the complexity of the verification problem is reasonably low, a SAT (satisfiability problem) solver could be used for verification.

During graphic user interface design, a cognitive walkthrough could be used for usability analysis. It is a structured inspection method for systematically analyzing designs to detect potential usability problems for specific tasks and user populations. The technicians responsible for updating tabling information and the user interface designer will participate in the cognitive walkthrough.

Software architecture and object-oriented methodology will be considered for the high-level and low-level software designs, respectively. The AcmeStudio, which is a visual environment for software architecture description, and the Acme ADL (Architectural Description Language) could be used for Software architecture design while the Rational Rose, which is a integrated environment for object-oriented methodologies and the UML (Unified Modeling Language) could be used for object-oriented methodology.

## Infrastructure plan

All the resources from the MSIT-SE program are available to the project. Computing resources available for this project are characterized as follows.

- Hardware: Intel Pentium III 1.0G/512MB RAM

- Operating System: Windows XP, Unix (on the CS machine) or Linux (on the Andrew machine)

- Applications: Microsoft Project

- Programming Environment: Java/Eclipse

- Site: Wean Hall 4615, Carnegie Mellon University

## Product acceptance plan

Every milestone of the project will be accepted formally by the client by signing appropriate acceptance documentation. The client will participate in the acceptance test and provide additional requests for changes and improvements.

# Supporting process plans

## Configuration management plan

This section shall contain the configuration management plan for the software project, to include the methods that will be used to provide configuration identification, control, status accounting, evaluation, and release management. In addition, it shall specify the processes of configuration management to include procedures for initial baselining of work products, logging and analysis of change requests, change control board procedures, tracking of changes in progress, and procedures for notifying concerned parties when baselines are first established or later changed. The configuration management process should be supported by on or more automated configuration management tools.

## Verification and validation plan

The verification and validation plan will be part of a separate document and will be maintained accordingly.

## Documentation plan

There are a number of documents that will be produced during the lifetime of the project. All documents are responsibility of the project staff. The list of documents that will be created and maintained under version control includes:

- Software project management plan

- Software requirement specification

- Software design specifications

- Risk management sheet

- Test scripts and results

- Meeting/review notes